## Action Plan
Development Action Plan
Project Name: | Alert Triage Workflow
Project Number: | #P1234
Project Manager: | XYZ
Action Item ID | Date Opened | Action Item | Assigned To | Dept. | Priority | Direction | Due Date | Issues | Resolution | Date Issue Resolved | Date Closed | % Complete | Status | Notes
1 | 12-Feb | Build Alert List View UI + API wiring | Frontend Dev | FE | High | Implement table, routing, severity tags | 18-Feb | None | N/A |  |  | 20 | In Progress | Use mock JSON until backend ready
2 | 12-Feb | Build Alert Detail View (metadata + layout) | Frontend Dev | FE | High | Connect list → detail navigation | 20-Feb | Waiting for schema | Placeholder fields | 13-Feb |  | 10 | Created
3 | 12-Feb | Implement Status Workflow | Backend Dev | BE | High | Create status update endpoint | 22-Feb | None | N/A |  |  | 0 | Not Started
4 | 12-Feb | Implement Notes API + Notes UI | Backend + FE | BE/FE | Medium | Add/fetch notes | 23-Feb | None | N/A |  |  | 0 | Not Started | MVP: No delete/edit
5 | 12-Feb | Integrate Quick Actions | Frontend Dev | FE | Medium | Add stubbed responses | 24-Feb | None | N/A |  |  | 0 | Not Started | Shows toast/messages
6 | 12-Feb | Add Playbook Action Buttons | Full-Stack Dev | FS | Medium | Stub POST responses | 26-Feb | None | N/A |  |  | 0 | Not Started | No automation required
7 | 12-Feb | Create Mock Backend Endpoints | Backend Dev | BE | High | Provide JSON to FE | 17-Feb | None | N/A |  |  | 30 | In Progress | Enables FE dev to start
8 | 12-Feb | Add Error Handling + Loaders | Frontend Dev | FE | Low | Implement empty/error states | 25-Feb | None | N/A |  |  | 0 | Not Started | Standard messages
9 | 12-Feb | QA Testing + Bug Triage | QA Engineer | QA | Medium | Full E2E testing | 28-Feb | Pending FE completion | TBD |  |  | 0 | Not Started | Includes regression